## Traceability Matrix
Requirements Traceability Matrix
BAHub — BusinessAnalysis.hopto.org
Req ID | Requirement Description | Priority | Source Stakeholder | Business Objective Ref | Design Element / Component | Test Case Reference | Implementation Status | Notes
REQ-001 | The system shall display real-time stock availability on the product detail page | High | Priya Patel | OBJ-002 (Customer Satisfaction) | ProductDetail.tsx — StockBadge component | TC-021, TC-022 | Complete | Deployed to staging; pending production sign-off
REQ-002 | The system shall validate customer credit limit before accepting an order | High | Sarah Chen | OBJ-001 (Operational Excellence) | OrderService.validateCreditLimit() | TC-035 | In Progress | Backend complete; frontend integration pending
REQ-003 | Customers shall receive an automated order confirmation email within 60 seconds | Medium | James Kowalski | OBJ-003 (Compliance) |  | TC-047 | Not Started | Gap: no design element assigned — action: IT Lead to confirm email service
REQ-004 | The portal shall support bulk order import via CSV (max 50 line items) | Low | Marcus Webb | OBJ-001 (Operational Excellence) |  |  | Not Started | Gap: design and test coverage missing — deferred to Phase 2 scope review
REQ-005 | All customer data shall be encrypted at rest using AES-256 | High | Marcus Webb | NFR-003 (Security) | Infrastructure config — DB encryption at rest | TC-089, TC-090 | Verified | Penetration test passed 2026-05-01

## GUIDANCE
Requirements Traceability Matrix — Guidance
Column | Purpose | Common Pitfalls
Req ID | Unique identifier. Format: REQ-NNN. Use consistent numbering. | Non-unique IDs cause merge conflicts when multiple BAs maintain the same RTM.
Priority | High / Medium / Low — based on business value and delivery risk. | All requirements marked High — forces triage conversations to become explicit.
Business Objective Ref | Links requirement to a strategic objective. Orphaned requirements should be challenged. | Requirements without an objective link are often gold-plating — trace back or remove.
Design Element | Specific component, module, or API that implements this requirement. | Vague entries like "backend" — be specific enough that a developer knows exactly what to look for.
Test Case Reference | Links to test case ID in test management tool. Blank = coverage gap (highlighted red). | Listing test cases that test the wrong thing — verify the test actually exercises the requirement.
Implementation Status | Not Started / In Progress / Complete / Verified. Verified = tested and accepted by business. | Marking "Complete" before business acceptance — complete means deployed, not just coded.
Gap Highlighting | Rows with blank Design Element OR Test Case are highlighted red automatically. | Ignoring red rows — each gap is a delivery risk that should be assigned and resolved.