## Risk Register
Risk Register
BAHub — BusinessAnalysis.hopto.org
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Mitigation Strategy | Contingency Plan | Owner | Status | Date Identified | Review Date
RISK-001 | ERP API integration complexity underestimated; scope creep in technical work | Technical | 3 | 4 |  |  | Run 2-week API spike before full build; define integration contract with IT Lead | Revert to CSV batch import as interim approach; accept 3-week delay | Marcus Webb | Mitigating | 2026-05-01 | 2026-06-01
RISK-002 | Low customer adoption of self-service portal reduces expected efficiency saving | Business | 2 | 4 |  |  | Co-design with top 20 customers; provide onboarding support for first 60 days | Retain parallel email channel for 90 days post go-live as fallback | Sarah Chen | Open | 2026-05-01 | 2026-07-01
RISK-003 | Peak season go-live conflicts with warehouse operations freeze period | External | 4 | 5 |  |  | Confirm go-live window with Operations Director; build 4-week buffer before peak | Delay go-live to post-peak season; extend parallel run period | Elena Torres | Open | 2026-05-10 | 2026-05-25
RISK-004 | Budget overrun due to unplanned infrastructure upgrades | Resource | 2 | 3 |  |  | IT Lead to confirm infrastructure readiness before detailed design sign-off | Request contingency budget approval from Finance (£50,000 reserve) | James Kowalski | Open | 2026-05-12 | 2026-06-15
RISK-005 | Third-party payment gateway provider changes API, breaking integration | External | 1 | 5 |  |  | Subscribe to gateway change-log notifications; pin to stable API version | Engage alternative gateway provider as contingency (Stripe evaluated) | Marcus Webb | Open | 2026-05-15 | 2026-07-15

## GUIDANCE
Risk Register — Guidance
Column | Purpose | Workshop Facilitation Tips
Probability (1-5) | 1=Very unlikely (<5%), 5=Near certain (>90%). Based on current controls. | Ask "If we did nothing about this, how likely is it to occur?" — removes the mitigation bias.
Impact (1-5) | 1=Negligible, 5=Project terminating. Score the WORST plausible outcome. | Use a consistent impact scale across all risks — financial, schedule, reputation, and legal dimensions.
Risk Score | Probability × Impact. Auto-calculated. Scores: Low<6, Medium 6-11, High 12-19, Critical ≥20. | Workshop tip: dot-vote on probability and impact independently, then reveal — reduces anchoring bias.
Mitigation Strategy | Actions that REDUCE probability or impact BEFORE the risk occurs. | Confusing mitigation (reduce likelihood) with contingency (respond after). Both are needed for high risks.
Contingency Plan | Actions taken IF the risk materialises. Pre-approved triggers speed response. | Contingency without a trigger condition — define the specific event that activates the contingency.
Status | Open: identified, not yet mitigated. Mitigating: mitigation underway. Closed: resolved or accepted. | Never close a risk without recording the resolution — it provides valuable lessons-learned data.
Risk workshops | Run 2-hour workshop with 6-8 participants covering: brainstorm, categorise, score, assign owners. | Include sceptics — the person most resistant to the project is often the best risk identifier.