## Stakeholder Matrix
Stakeholder Analysis Matrix
BAHub — BusinessAnalysis.hopto.org
Stakeholder Name | Role / Title | Organisation | Power (1-5) | Interest (1-5) | P-I Quadrant | Comms Preference | Key Concerns & Motivations | Resistance Factors | Engagement Strategy | Last Contact | Next Action
Sarah Chen | Chief Operating Officer | Acme Corp | 5 | 4 |  | Monthly steering report + email | Operational efficiency, cost reduction, risk avoidance | Concerns about transition disruption during peak season | Monthly 1-1 briefings; early involvement in scope decisions | 2026-05-10 | Share Phase 1 plan by 2026-06-01
Marcus Webb | IT Director | Acme Corp | 4 | 5 |  | Email + Jira tickets | Technical quality, security, team capacity | Prefers phased rollout; concerned about ERP integration complexity | Include in technical design reviews; pair with lead developer | 2026-05-18 | API capability confirmation by 2026-05-30
Priya Patel | Head of Customer Services | Acme Corp | 3 | 4 |  | Weekly team meetings | Customer experience, call volume reduction | Worried portal will increase call centre volume during transition | Co-design customer UAT; include in comms planning | 2026-05-12 | UAT planning session 2026-06-10
James Kowalski | Finance Director | Acme Corp | 4 | 2 |  | Monthly board report | ROI, budget adherence, audit trail | Sceptical of benefits realisation timeline | Quarterly financial review; link to approved business case | 2026-04-30 | Send updated NPV model by 2026-06-15
Elena Torres | Warehouse Operations Manager | Acme Corp | 2 | 5 |  | Daily stand-ups + Slack | Process clarity, training quality, minimal disruption | Concerned about WMS changes during peak order period | Include in process design workshops; pilot new process with her team | 2026-05-20 | Process walkthrough workshop 2026-06-05

## GUIDANCE
Stakeholder Analysis Matrix — Guidance
Column | Purpose | Common Pitfalls
Power (1-5) | 1=No influence, 5=Can veto or mandate decisions. Assess formal authority + informal influence. | Conflating seniority with power — a junior SME may have high influence over technical decisions.
Interest (1-5) | 1=Indifferent to outcomes, 5=Directly affected and highly engaged. | Assuming all executives have high interest — some are nominally involved but actually disengaged.
P-I Quadrant | Auto-calculated: Power≥3 AND Interest≥3 = Manage Closely. Adjust strategy accordingly. | Treating the quadrant as fixed — stakeholder positions shift as projects progress; review monthly.
Engagement Strategy | Specific actions tailored to the stakeholder's quadrant and concerns. | Generic strategies like "keep informed" without specifying how, when, and what channel.
Resistance Factors | Anticipate objections before they surface. Source from stakeholder interviews. | Assuming resistance is irrational — usually there is a legitimate concern that should be addressed.
Last Contact / Next Action | Track engagement cadence. Gaps in engagement = growing risk. | Not updating the register — a stale register provides false assurance.